## Sheet2
RACI
Project Deliverables | Ankit | Aravind | Sameer | Venkat | Resource | Roles and Responsibility
Project Planning |  |  |  |  | Ankit | Overall Project Management, Cloud Architecture Design, ETL, Datawarehouse Design, Monitoring Dashboard Design, QA
Define project scope and objectives | R, A | C | C | C | Aravind | Data Acquisition– Source 1, Datawarehouse Development, Unit Testing and UAT
Develop project schedule and plan | R, A | C | C | C | Sameer | Overall ETL Development,Reports & Dashboard Development,Unit Testing and UAT
Budget for Data Acquisition and Cloud Deployment | R, A | I | I | I | Venkat | Data Acquisition – Source 2,Cloud Integration,Unit Testing and UAT
Requirements Gathering
Conduct business requirements gathering sessions | R, A | C | C | C | R - Responsible
Define Acquisition and Data Profilling | R, A | R (Source 1), A | - | R (Source 2), A | A - Accountable
Prepare data requirements document | R, A | C | R | C | C - Consulted
Data Modeling |  |  |  |  | I - Informed
Design Conceptual model and ER Diagram | R, A | C | R | C
Define data transformations and ETL mappings | R, A | R (Source 1), A | R | R (Source 2), A
Review and approve data model | R, A | C | C | C
ETL Development
Develop ETL processes and scripts | R | R (Source 1), A | R, A | R (Source 2), A
Unit testing and code reviews | R, A | R | R, A | R
Data Warehouse Build
Install and configure data warehouse application (DDL Scripts) | R, A | R, A | R (Cloud Integration), A | R (Cloud Integration), A
Create and populate database objects | R, A | R, A | R | R
Performance tuning and optimization | R, A | C | C | C
Testing and Deployment
Develop test plans and test cases | R, A | R | R | R
Execute system testing and user acceptance testing | R, A | R | R | R
Verify Deployment | R, A | C | C | C
Reporting and Dashboards
Design reports and dashboards | R, A | C | C | R, A
Implement reports and dashboards | R, A | C | R, A | C
Project Presentation
Slide Deck Preperation | R, A | R | R | R
Maintainence & Support
Source Code Handover (Git Repository) | R, A | C | C | R
Provide ongoing support and maintenance | R, A | R | R | R